| Complexity | Characteristics | Estimated timing | What timing allows for | Factors that affect timing | Urgent bills |
| --- | --- | --- | --- | --- | --- |
| Low | - small to moderate number of provisions to be drafted or amended (up to 20) - easy to identify what amendments are needed - some analysis or research may be required - can be addressed by applying well-established or readily determinable drafting practices - will usually require only 1 or 2 drafts to finalise | 1-2 months | The estimated timings are from first instructions to providing a final copy for Cabinet The estimated timings allow for— - drafting (for information about the drafting process, see Developing Legislation and Working with PCO, pp 19-20). The extent of consequential amendments or transitional amendments may increase the time required to draft - clearance within your directorate - undertaking quality assurance checks to prepare a final version of the bill (for information about the QAC process, see Developing Legislation and Working with PCO, p 21) - your bill to be prioritised appropriately with other bills on the Legislation Program and other drafting and editing work of the office | Many factors beyond the time needed to draft a bill affect the time it takes to develop a bill Examples include— - how well developed the policy is—unresolved policy issues will generally increase drafting time, sometimes significantly - whether you have policy approval—changes in the policy approach once drafting has started will generally increase drafting time, sometimes significantly - how clear and complete your instructions are (for information about preparing instructions, see Developing Legislation and Working with PCO, pp 15-18) - whether you need to consult on your legislative proposal and who you need to consult (for information about who to consult on legislative proposals, see Developing Legislation and Working with PCO, pp 11-12) - whether your legislative proposal engages human rights, includes offences or otherwise involves political or other sensitivities—resolving these issues during the drafting process will generally increase drafting time - your capacity to respond to drafts and queries from your drafting team | If your bill is urgent, we can work with you to ensure your bill meets the required timeframe However, be aware that compressing the time to develop a legislative proposal or draft a bill of medium or high complexity may impact the quality of the overall product, for example, by— - reducing our capacity to help you identify gaps, solve problems and find the best legislative solution - reducing your time to obtain advice on issues arising from the proposal, such as human rights, offences or other legal issues, which may only become apparent during the drafting process - reducing our capacity to undertake quality assurance checks and ensure consistency with the statute book and current drafting practice Risks of compressing the time to develop legislative proposals or draft bills include— - comments from the Scrutiny Committee requiring a response from your Minister - increased likelihood of the need for Assembly amendments - legislation that doesn’t operate as intended or needs to be subsequently amended We can work with you to identify options to reduce these risks, including whether elements of the legislative proposal can be progressed separately (for example, a bill dealing with consequential and transitional amendments) |
| Medium | - may involve a reasonable number of provisions to be drafted or amended (20 to 80), or smaller number of complex amendments/smaller complex bill - reasonable amount of work may be required to identify what the policy intention is or what amendments are needed - reasonable amount of analysis or research required - may involve a degree of originality or careful application of precedents and drafting practices | 3-6 months |  |  |  |
| High | - generally involves a large number of provisions to be drafted or amended (over 80), but may involve a smaller number of highly complex amendments - significant work may be required to identify what the policy intention is or what amendments are needed - significant analysis or research required to identify appropriate legislative solution - often involves significant political or other sensitivities - involves a high degree of originality or careful application of precedents and drafting practices | 6 + months |  |  |  |

https://www.pco.act.gov.au/__data/assets/pdf_file/0003/2216037/Developing-Legislation-and-Working-with-PCO.pdf